# Acceptance Criteria

Introduction

This Attachment 01 to this Agreement is a significant and mandatory component that in combination with the other Appendices in this Agreement describe how the Transition and Improvement shall be accomplished.

Objective of the document

The objective of this Attachment 01 is to fully document Milestones, Deliverables and Acceptance Criteria that are agreed between the Parties prior to or at Plan Readiness Date for the Transition Project and Improvements.

Milestones and Acceptance Criteria agreed

| Milestone # | Milestone name | Duration of Review Period | Acceptance Criteria | Agreed date |
| --- | --- | --- | --- | --- |
| N/A | Signature date | N/A | N/A | N/A |
| M0 | Planning commencement date | 3 Working Days unless otherwise agreed | Vendor´s Transition Project team mobilized onsite, at the Customer´s location, for the Discovery and Planning Phase Vendor has organized and scheduled a kick-off to align all relevant parties on the Discovery and Planning Phase Plan for the Discovery and Planning Phase agreed and signed off High-level delivery plan for Transition Project agreed and signed off Interim Transition Project governance and monitoring procedures established |  |
| M1 and M2 | Improvement & Transition Plan Readiness | 5 Working days | Vendor´s project team as agreed during the RFP process shall be mobilized on-site for the subsequent phases Detailed plans for subsequent phases (Improvement plan and/or Transition Project plan) agreed and signed off, including (but not limited to): - All Milestones, Deliverables and Acceptance Criteria - All knowledge transfer and training activities - All design, build and roll-out activities - All test and verification activities including Customer´s UAT - All relevant cutover and fallback related activities - All Customer review and re-verification activities - All project coordination, project management and project communication activities - All governance-related activities - All activities set out in time and assigned to a responsible Party - All Parties’ efforts specified Templates, procedures, documentation and reporting established, as and when needed from the outset of the Improvement Phase and Establishment Phase Transition governance and monitoring (including all Transition Project and Improvements roles) fully established; no unresolved issues |  |
| M2 | Discovery Report approval | 3 Working Days | A final copy of Discovery Report has been completed which includes design, architecture of the products which are to be improved or implemented and the process for rolling out new products. The discovery report shall also include principles for implementing change in the Customer´s organization for best practice use of the product. The report shall provide guidance for communication management, building Customer´s competence in using the products, and managing the technology. |  |
| M3 | Technology establishment criteria | 10 Working Days | Agreed Vendor Deliverables including all relevant software, hardware and tools have been successfully implemented, transformed and rolled out to agreed Customer recipients, agreed Customer personnel and relevant third parties so that the Solution are available and ready for daily use. The Vendor has verified the success of the roll-out and documented this verification in any necessary verification reports including any necessary integration and regression test reports for dependent Services rolled out at prior commencement dates: and including any required User Acceptance Test (UAT) reports for Services rolled out at this Commencement Date. The Vendor has delivered any necessary Deliverable documentation including the knowledge transfer documentation (Application Overview Document/ Technical Overview Document) with details of the information received as part of preparation phase. The Vendor has established all parts of the Collaboration Model necessary for the intended day-to-day use of the rolled-out Vendor Deliverables. The Vendor has established all parts of the Engagement Model necessary for the intended day-to-day use of the rolled-out Vendor Deliverables. |  |
| M3 | Operational Readiness criteria prior to start of the approval phase. | TBD in planning phase | - Every time the Solution is rolled out to all users it will undergo a User Acceptance Testing process - User satisfaction of the new or updated technology which has been rolled out is measured to be equal to or greater than 65%. - 75% of the users have been trained on the new or updated technology that is being rolled out. - 100% of the Super Users have been trained on the technology - 100% of Management resources with personnel responsibility have been offered training tailored to how they can champion the change towards its employees - Knowledge transfer for maintenance completed for NRK’s workplace and security teams and service desk. - All category A or B errors, identified during User Acceptance Testing, have been fixed and tested before the roll-out - A continuous improvement plan has been created to follow up on readiness assessment and UAT - All documentation for user self-service and training is in place. - All processes and workplace have been updated to the new solutions |  |